BENUE STATE GOVERNMENT OF NIGERIA

BENUE STATE UNIVERSAL BASIC EDUCATION BOARD, MAKURDI

WORK PLAN - 2025

Address: Opposite Ministry of Agriculture,

P.M.B. 102070 Makurdi

E-Mail: benuesubeb2024@gmail.com

Official Phone Number: 08105548728

SLOGAN: The Food Basket of the Nation

December, 2024

Foreword

The Benue State 2025 Work Plan epitomizes our collective vision and unwavering commitment to sculpting a brighter future for the Benue Child through a comprehensive approach to Basic Education.

Under the stewardship of His Excellency, the Governor of Benue State, Rev. Fr. Dr. Hyacinth Iormem Alia, our State has embarked on a transformative journey towards establishing an education system that empowers our youth and positions them for success in an ever-evolving world. His agenda underscores the paramount importance of inclusive, equitable, and high-quality education for all, reinforcing our conviction that education is a potent tool for individuals and societal advancement.

The 2025 Work Plan reflects our resolute dedication to these core principles. The Benue State Universal Basic Education Board (SUBEB) is deeply committed to actualizing this plan. Our vision is to ensure that every child in Benue State has access to a robust educational foundation, nurturing a lifelong passion for learning and preparing them to become active, contributing members to our society.

The State has conscientiously endeavoured to align the Work Plan with the required indices, aspiring to achieve Universal Basic Education and promote inclusive education.

The successful implementation of this plan necessitates collaboration and partnership across all levels of government, educators, parents, and other stakeholders. My sincere appreciation to the Benue State Government for their invaluable contributions, as well as to various departments, and agencies, Federal Government and International Development Partners (IDPs) on our journey towards providing quality education for self-reliance and productivity.

Lastly, I commend the department of Planning, Research, and Statistics (PRS) at the Benue State Universal Basic Education Board for the development of the Work Plan. Their dedication has made this Work Plan a reality.

Dr. Grace Adagba

Executive Chairman,

Benue State Universal Basic Education Board.

December, 2024.

Acknowledgement

The development of the Basic Education Work Plan - 2025 could not have been actualized without the commitment of the Benue State Government and collaborative efforts of critical stakeholders working together to deliver Basic Education to the Benue Child. Thus, there is need to acknowledge and commend the efforts of the Executive Chairman, State Universal Basic Education Board, Dr. Grace Adagba, and the Hon. Commissioner for Education and Knowledge Management.

A very special gratitude goes to Benue SUBEB Management team, for their immense support for the actualization of this work plan. My sincere appreciation goes to the International Development Partners (IDPs); worthy to mention are the United Nations Children Fund (UNICEF), Better Education Service Delivery for All (BESDA), the United Nations Scientific Cultural Organisation (UNESCO), World Bank and Consultants, who have partnered with SUBEBs to ensure the success of Basic Education. Also to recognised are the State Ministry of Education and Knowledge Management (MoE&KM), SUBEB Strategic Planning Desk Officer, Mr. Ker Simon Terhide, and the entire Planning Staff, EMIS Staff, Education Secretaries (ESs), NUT, AOPSHON, NGOs, CSOs, all Directors/Departments of Benue SUBEB and everyone who have been a part of the development process are not left out in our gratitude for their commitment, contributions and hard work.

This acknowledgement will not be complete without appreciating the moral support of my wife, Mrs. Doowuese Akura and my Children.

Above all, I thank God Almighty, for the opportunity to produce this work plan, for Benue Public Basic Education.

Akura Terkimbi

Director, Planning, Research, and Statistics

Benue State Universal Basic Education Board December, 2024.

TABLE OF CONTENTS

Foreword	-	-	-	-	-	-	-	-	-	i

Acknowledgement	-	-	-	-	-	-	-	-	ii

Table of Contents	-	-	-	-	-	-	-	-	iii

1.0	INTRODUCTION	-	-	-	-	-	-	-	-	-	1

2.0	BENUE SUBEB WORK PLAN-2025 OBJECTIVES AND GOALS	-	-	-	1

3.0	BENUE SUBEB WORK PLAN-2025 TIMELINE	-	-	-	-	-	1

4.0	ESTIMATED COST FOR PRIORITY PROGRAMMES PLAN	-	-	-	-	1

4.1	POLICY 1: ACCESS, EQUITY AND INCLUSIVENESS	-	-	-	-	-	2

4.1.1	POLICY OBJECTIVE	-	-	-	-	-	-	-	-	2

4.2	POLICY 2: QUALITY AND EFFICIENCY	-	-	-	-	-	-	4

4.2.1	POLICY OBJECTIVE	-	-	-	-	-	-	-	-	4

4.3	POLICY 3: SYSTEM STRENGHTENING AND EFFICICIENCY	-	-	-	-	10

4.3.1	POLICY OBJECTIVE	-	-	-	-	-	-	-	-	10

5.0	SUMMARY OF POLICY OBJECTIVE COSTS	-	-	-	-	-	-	11

6.0	ASSUMPTIONS AND COSTS PROJECTIONS	-	-	-	-	-	11

7.0	COST OF THE SUB-SECTOR PLAN FOR BENUE SUBEB WORK PLAN	-	-	-	12

8.0	RISKS AND MITIGATION MEASURES	-	-	-	-	-	-	13

9.0	MONITORING AND EVALUATION	-	-	-	-	-	-	15

10.0	KEY PERFORMANCE INDICATORS	-	-	-	-	-	-	15

11.0	CONCLUSION	-	-	-	-	-	-	-	-	-	20

1.0	INTRODUCTION

Planning for Basic Education aimed principally at opening more access, ensuring quality, efficiency, strengthening the education sub-sectors and financing the public basic education at all levels, with better policies and strategies to grant free education to all children of basic school going-age.

The Benue SUBEB Work Plan-2025 basically covers Public Basic Education Sector; Pre-Primary, Primary, and Junior Secondary School levels in Benue State; represents the activities, policy objectives, outputs, outcomes, strategies, annual outputs targets, cost implications and monitoring and evaluations under the pillars and policies of: Access, Equity and Inclusiveness; Quality and Efficiency; System Strengthening and Efficiency; and Sustainable Funding.

2.0	BENUE SUBEB WORK PLAN-2025 OBJECTIVES AND GOALS

With the vision and mission - “To evolve a deliberate Policy in education at the foundation level where the right person does the right thing at the right time and knows for what and to whom he/she is responsible” and “To bequeath to posterity a sound academic background that is capable of sustaining their future enthusiasm” respectively guilds the 2025 Benue SUBEB Work Plan objectives targeted at, for a visual reference, as a driving force to a right foot start, with purpose fulfilling achievements. The objectives include:

- To cub and close every possible gap(s) affecting Access, Equity and Inclusiveness to Public Basic Education in the state.

- To improve teaching and learning, by the provision of relevant resources and materials within a given time, for an efficient Public Basic Education in Benue State.

- To ensure proper coordination for development and management of Public Basic Education in Benue State.

- Setting a responsible financial investment funding and anticipation of desired support to develop Public Basic Education in Benue State.

The above objectives under the pillars of Access and Equity, Quality and Relevance, System Strengthening and Unsustainable Funding will make the public basic education sector more responsive to emerging state/national needs with the changing global circumstances. And Benue SUBEB focuses on its Work Plan-2025 to effectively and efficiently harness necessary resources to achieve outputs/outcomes; goals/programmes within a well-defined monitoring and time frameworks.

3.0	BENUE SUBEB WORK PLAN-2025 TIMELINE

This Benue SUBEB Work Plan-2025 pays attention to the trend of availability of funds over a given period of One year (2025), from January, 2025 to November, 2025 and helps to project the funds that the state may likely receive from various sources and how they can be used to solve the various recurring challenges of Public Basic Education in the state.

4.0	ESTIMATED COST FOR PRIORITY PROGRAMMES PLAN

The Benue SUBEB Work Plan-2025 interacts with the pillars of access, equity, inclusiveness, quality, efficiency, strengthening and funding giving specific activities, targets and outputs within One (1) Year (2025). The aim is to achieve desired success, also commitment with Benue State Government and other relevant agencies are harmonized responsibly.

4.1	POLICY 1: ACCESS, EQUITY AND INCLUSIVENESS

4.1.1	POLICY OBJECTIVE: To cub/close every possible gap(s) affecting Access, Equity and Inclusiveness to Public Basic Education in the state.

Table 4.1: Access, Equity and Inclusiveness

| S/N | ACTIVITIES | OUTPUTS | OUTCOMES | INDICATOR | OUTPUT TARGET | COSTS (NGN ‘000’) |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | 2025 | 2025 |
| 1 | Construction and Distribution of 7,800No. Dual Desk and Chair of Steel/Wood | 7,800No. Dual Desk and Chair of Steel/Wood constructed & distributed | Enhanced sitting capacity | 75% achieved | 7,800No. Dual Desk and Chair of Steel/Wood | 1,317,630,600.00 |
| 2 | Procurement/Supply of 64No. sets 1-Tables/4-Chairs of ECCDE Plastic. | 64No. sets 1-Tables/4-Chairs of ECCDE Plastic procured & supplied | Enhanced sitting capacity | 75% achieved | 64No. sets 1-Tables/4-Chairs of ECCDE Plastic. | 8,884,355.60 |
| 3 | Construction and Distribution of 64No. Set of Library 1-Tables and 4-Chairs of Steel/Wood | 64No. Set of Library 1-Tables and 4-Chairs of Steel/Wood constructed & distributed | Enhanced sitting capacity | 75% achieved | 64No. Set of Library 1-Tables and 4-Chairs of Steel/Wood | 35,753,600.00 |
| 4 | Purchase and supply of 4No. Book Steel shelves | 4No. Book Steel shelves purchased | Reading culture improved | 75% achieved | of 4No. Book Steel shelves | 3,090,000.00 |
| 5 | Construction and Distribution of Set of Library 1-Tables and 2-Chairs of Steel/Wood | 1-Tables and 2-Chairs of Steel/Wood constructed & distributed | Provision of Adequate Furniture for Pupils and Teachers. | 75% achieved | 1-Tables and 2-Chairs of Steel/Wood | 50,793,600.00 |
| 6 | Construction of 4No. Storey building block of 4 classrooms, 3 Offices, 2 Libraries, Store, Play room and 10 Water closet | 4 No, storey building block of 4 classroom, 3 Offices, 2 Libraries, Store, play room and 10 Water closet constructed | Ensure Equity and inclusiveness | 75% achieved within 3 months | 4No. Storey building block of 4 classrooms, 3 Offices, 2 Libraries, Store, Play room and 10 Water closet | 811,282,311.52 |
| 7 | Construction of 20 Unit UBE Standard Block of 3 Classrooms, Office, Store & Block of VIP Toilets | 20 Unit UBE Standard Block of 3 Classrooms, Office, Store & Block of VIP Toilets constructed | Ensure Equity and inclusiveness | 75% achieved within 3 months | 20 Unit UBE Standard Block of 3 Classrooms, Office, Store & Block of VIP Toilets | 1,783,401,885.60 |
| 8 | Construction of 6 No. Perimeter fence and Gate house & Toilets | 6 No. Perimeter fence and Gate house & Toilets Type C constructed | Security enhanced | 75% achieved within 3 months | 6 No. Perimeter fence and Gate house & Toilets | 618,114,100.52 |
| 9 | Reconstruction/Renovation of 47No. Blocks of 128No Classrooms, 23No Offices, 23No stores, 1No staffroom, 1No. Library, 1No.500M Parameter Fence and 1No playroom. | 47No. Blocks of 128No Classrooms,23No Offices, 23No stores, 1No staffroom, 1No. Library, 1No.500M Parameter Fence and 1No playroom reconstructed. | Ensure Equity and inclusiveness | 75% achieved within 3 months | 47No. Blocks of 128No Classrooms,23No Offices, 23No stores, 1No staffroom, 1No. Library, 1No.500M Parameter Fence and 1No playroom | 1,768,139,111.13 |

| S/N | ACTIVITIES | OUTPUTS | OUTCOMES | INDICATOR | OUTPUT TARGET | COSTS (NGN ‘000’) |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | 2025 | 2025 |
| 10 | Sinking of 3no. Boreholes, construction of Overhead, Solar Rack, wire fence and 2000 litres PVC Tank | 3no. Boreholes, construction of Overhead, Solar Rack, wire fence and 2000 litres PVC Tank sinked | Provision of Adequate WASH Facilities. | 75% achieved | 3no. Boreholes, construction of Overhead, Solar Rack, wire fence and 2000 litres PVC Tank | 49,165,615.05 |
| 11 | Construction of 8 Unit of a 3No block of VIP Toilets | 8 Unit of a 3No block of VIP Toilets constructed | Provision of Adequate WASH Facilities. | 75% achieved | 8 Unit of a 3No block of VIP Toilets | 164,112,940.00 |
| 12 | Routine Inspection visits to all the Project Sites. | Inspection visits to all the Project Sites carried out | Project Monitoring | 75% achieved | Inspection visits to all the Project Sites | 142,185,703.38 |
| 13 | Increase enrolment in ECCDE, primary and JSS schools through advocacies and sensitizations | enrolment in ECCD, primary and JSS schools through advocacies and sensitizations increased | Out of school children reduced and GER increased. | Increased GER by 30% | Enrolment in ECCD, primary and JSS schools through advocacies and sensitizations | 10,000,000.00 |
| 14 | Procurement of 20,519 Pupil’s furniture | 20,519 Pupil’s furniture procured | Out of school children reduced and GER increased. | Increase enrolment by 25% | 20,519 Pupil’s furniture | 3,115,297,175.00 |
| 15 | Procurement of 821 Teacher’s furniture | 821 Teacher’s furniture procured | Improve on teachers’ furniture | Increase enrolment by 25% | 821 Teacher’s furniture | 86,492,350.00 |
| 16 | Carry out advocacy and sensitization to Increase enrolment of children with special needs | Enrolment of children with special needs increased by 25% | Out of school children reduced and GER increased. | Increased GER by 25% | Enrolment of children with special needs | 7,000,000.00 |
| 17 | Carry out sensitization towards enrolment in Emergency IDPs Schools Program. | sensitization towards enrolment in Emergency IDPs Schools Program carried out | Out of school children reduced and GER increased. | 100% Enrolment of Basic Education School Age Children in Emergency IDPs Camps. | enrolment in Emergency IDPs Schools Program | 7,000,000.00 |
| 18 | 1 No. TOYOTA HILUX van 2025 model | 1 No. TOYOTA HILUX purchased | For effective coverage of SBMC activities | 75% achieved | 1 No. TOYOTA HILUX | 149,779,220.47 |
| 19 | Provide Award to Pupils who successfully transit from one level to another. | Award to Pupils who successfully transit from one level to another provided | Drop- out and Out-of-School children reduced and GER increased | Increased GER by 25% | Award to Pupils who successfully transit from one level to another | 20,000,000.00 |
| 20 | Girl Child's Education and Monitoring/Evaluation (M&E) of Girl Child's progress in Schools. | Monitoring/Evaluation (M&E) of Girl Child's progress in Schools increased | Reduced Girl Child Parity Gap and Develop Girl Child in our Public Basic Schools. | Reduce Gender gap by 15% | Monitoring/Evaluation (M&E) of Girl Child's progress in Schools | 17,000,000.00 |
| 21 | Celebrate International Day of the Girl Child | International Day of the Girl Child celebrated | Public Basic School Girls sensitized triggered for development. | Feedback/Report in Percentages of responses. | International Day of the Girl Child | 8,000,000.00 |
|  | ACEESS, EQUITY AND INCLUSIVENESS SUB-TOTAL |  |  |  |  | 10,173,122,568.27 |

4.2	POLICY 2: QUALITY AND EFFICIENCY

4.2.1	POLICY OBJECTIVE: To improve teaching/learning, by the provision of relevant resources and materials within a given time, for an efficient Public Basic Education in Benue State.

Table 4.2: Quality and Efficiency

| S/N | ACTIVITIES | OUTPUTS | OUTCOMES | INDICATOR | OUTPUT TARGET | COSTS (NGN ‘000’) |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | 2025 | 2025 |
| 1 | Recruitment and deployment of 9,700 teachers in rural communities | 9,700 teachers in rural communities recruited and deployed | Enhanced teaching/learning activities | 40% achieved | 9,700 teachers in rural communities | 1,552,000,000 |
| 2 | Train teachers and mentors on Structured Pedagogical Package (SPP) in the 23 LGEAs | At least 9,700 teachers and mentors trained on Structured Pedagogical Package (SPP) | Enhanced teaching/learning activities | 90% achieved | 9,700 teachers and mentors | 989,400,000.20 |
| 3 | Procure Teaching Learning Materials (TLMs) English/Mathematics/Workbook) | At least 84,000 TLMs procured | Enhanced teaching/learning activities | 75% achieved | 84,000 TLMs | 722,400,000 |
| 4 | Procurement and supply of 3,292 Tablets for Primary and Junior secondary schools in the state | 3,292 Tablets for Primary and Junior secondary schools in the state procured | Enhanced Digital teaching/learning | 80% achieved | 3,292 Tablets for Primary and Junior secondary schools in the state | 2,139,800,000 |
| 5 | Procurement and supply of 20 Computers for SUBEB Headquarters | 20 Computers for SUBEB Headquarters procured | To strengthen EMIS and Data processing | 75% achieved | 20 Computers for SUBEB Headquarters | 20,000,000 |
| 6 | Procuring 12,000 copies of revised Basic Education Curriculum | 12,000 copies of revised Basic Education Curriculum procured | Enhance Teaching/Learning | 75% achieved | 12,000 copies of revised Basic Education Curriculum | 99,529,992.37 |
| 7 | GSCCI Pillar 1: Carrying out Greening of Schools/Planting of trees (GSCCI) | Greening of Schools/Planting of trees (GSCCI) carried out | Ensure beauty of school environment | 75% achieved | Greening of Schools/Planting of trees | 29,999,296.00 |
| 8 | GSCCI Pillar 2: Promoting Entrepreneurial Greening Curricula in Basic Schools in the State. | Greening Curricula in Basic Schools in the State promoted. | Ensure sustainability of Greening | 75% achieved | Greening Curricula in Basic Schools in the State | 1,501,856.80 |

| S/N | ACTIVITIES | OUTPUTS | OUTCOMES | INDICATOR | OUTPUT TARGET | COSTS (NGN ‘000’) |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | 2025 | 2025 |
| 8 | GSCCI Pillar 2: Promoting Entrepreneurial Greening Curricula in Basic Schools in the State. | Greening Curricula in Basic Schools in the State promoted. | Ensure sustainability of Greening | 75% achieved | Greening Curricula in Basic Schools in the State | 1,501,856.80 |
| 9 | GSCCI Pillar 3: Carry out Teacher training and education system capacity. | Teacher training and education system capacity carried out | Ensure sustainability of Greening | 75% achieved | Teacher training and education system capacity. | 8,160,000.00 |
| 10 | GSCCI Pillar 4: Extend Greening to host communities | Greening to host communities carried out | Ensure sustainability of Greening | 75% achieved | Greening to host communities | 11,748,559.17 |
| 11 | GSCCI Pillar 5: Participation at National Greening competitions | National Greening competitions attended | Ensure sustainability of Greening | 75% achieved | National Greening competitions | 8,183,139.72 |
| 12 | GSCCI Pillar 6: Establish Green Clubs (Climate change clubs) in public schools across the state | Green Clubs (Climate change clubs established | Ensure sustainability of Greening | 75% achieved | Green Clubs (Climate change clubs) | 11,500,000.00 |
| 13 | Ensure Safeguards and Waste Management Initiatives | Safeguards and Waste Management Initiatives ensured | Adopt to Climate change | 75% achieved | Safeguards and Waste Management Initiatives | 23,592,851.69 |
| 14 | Carry out Supervision and monitoring of GSCCS Initiatives | Supervision and monitoring of GSCCS Initiatives carried out | Ensure sustainability of Greening | 75% achieved | Supervision and monitoring of GSCCS Initiatives | 47,500,000.00 |
| 15 | Procurement of Unified/Same Uniforms for Pupils of Benue State Public Basic Education Schools. | Unified/Same Uniforms for Pupils of Benue State Public Basic Education Schools procured | Ensure Identity/Uniformity | 25% achieved | Unified/Same Uniforms for Pupils of Benue State Public Basic Education Schools | 785,126,000.00 |
| 16 | Procurement and supply of 29 Computers for the 23 LGEA Headquarters and 6 Zonal offices | 23 Computers for the 29 LGEA Headquarters procured | To strengthen EMIS and Data processing | 25% achieved | 29 Computers for the 23 LGEA Headquarters and 6 Zonal Offices | 29,000,000 |

| S/N | ACTIVITIES | OUTPUTS | OUTCOMES | INDICATOR | OUTPUT TARGET | COSTS (NGN ‘000’) |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | 2025 | 2025 |
| 17 | Train 1150 6teachers on Jolly Phonics in cluster school model | 1150 teachers trained on Jolly Phonics in cluster school model | Teachers’ capacity improved | 30% achieved | 1150 teachers on Jolly Phonics in cluster school model | 69,000,000.00 |
| 18 | Train 230 teachers trained on Strengthening Mathematics and Science Education (SMASE) | 230 teachers trained on Strengthening Mathematics and Science Education (SMASE) | Teachers’ capacity improved | 25% achieved | 230 teachers on Strengthening Mathematics and Science Education (SMASE) | 13,800,000.00 |
| 19 | Train 200 teachers trained on Cluster Support Mechanism | 200 teachers trained on Cluster Support Mechanism | Teachers’ capacity improved | 25% achieved | 200 teachers on Cluster Support Mechanism | 12,000,000.00 |
| 20 | Procurement/Supply of Sporting equipment and Organising sport tournaments. | Sporting equipment and Organising sport tournaments. procured | Grassroots sports development &talents hunt. | 75% achieved | Sporting equipment and Organising sport tournaments | 71,092,851.69 |
| 21 | Inter-school competition | Inter-school competition carried out | Grassroots sports talents developed & talent hunt | 75% achieved | Inter-school competition | 500,000.00 |
| 22 | LGEA competition | LGEA competition carried out | Grassroots sports talents developed & talent hunt | 75% achieved | LGEA competition | 600,000.00 |
| 23 | Zonal competition | Zonal competition carried out | Grassroots sports talents developed & talent hunt | 75% achieved | Zonal competition | 800,000.00 |
| 24 | State final | State final carried out | Grassroots sports talents developed & talent hunt | 75% achieved | State final | 5,463,106.08 |
| 25 | Customize Track suit | Customize Track suit procured | Increase access to sporting opportunities | 75% achieved | Customize Track suit | 6,500,000.00 |
| 26 | Geopolitical competition | Geopolitical competition carried out | develop pupils’ skills as sportsmanship | 75% achieved | Geopolitical competition | 3,199,178.33 |
| 27 | (10 %) Set Aside for National Finals | National Finals carried out | develop pupils’ skills as sportsmanship | 75% achieved | National Finals | 2,123,785.55 |

| S/N | ACTIVITIES | OUTPUTS | OUTCOMES | INDICATOR | OUTPUT TARGET | COSTS (NGN ‘000’) |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | 2025 | 2025 |
| 28 | Other sports competitions e.g. NSSF | Other sports competitions carried out | develop pupils’ skills as sportsmanship | 75% achieved | Other sports competitions | 2,123,785.55 |
| 29 | Electronic Media | Electronic Media used | Educate, inform and entertain the general public on important activities organized by SUBEB/UBEC | 75% achieved | Electronic Media | 1,554,642.59 |
| 30 | Printing Media | Printing Media used | Educate, inform and entertain the general public on important activities organized by SUBEB/UBEC | 75% achieved | Printing Media | 500,000.00 |
| 31 | Customize Shirt | Customize Shirt used | Increase access to sporting opportunities | 75% achieved | Customize Shirt | 1,000,000.00 |
| 32 | Social media | Social media | Educate, inform and entertain the general public on important activities organized by SUBEB/UBEC | 75% achieved | Social media | 500,000.00 |
| 33 | Conduct of CQA for 9 weeks to visit Schools by UBEC, SUBEB and LGEAs for evaluation of 144 Schools | CQA for 9 weeks to visit schools by UBEC, SUBEB and LGEAs for evaluation of 144 Schools carried out | For effective coverage of target schools | 75% achieved | CQA for 9 weeks to visit Schools by UBEC, SUBEB and LGEAs for evaluation of 144 Schools | 12,502,372.38 |
| 34 | Train 450 QA Officers and School Administrators on New Methodology of Monitoring and Evaluation of Teaching and Learning in Benue Public Primary Schools and JSS. | 450 QA Officers and School Administrators’ Trained | Ensure Improved Quality of Teaching/Learning. | 75% achieved | 450 QA Officers and School Administrators’ | 8,400,000.00 |

| S/N | ACTIVITIES | OUTPUTS | OUTCOMES | INDICATOR | OUTPUT TARGET | COSTS (NGN ‘000’) |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | 2025 | 2025 |
| 35 | Procurement/Supply of Agricultural equipment, Farm inputs, Seedlings, Books, Flyers and journals/Organization of sensitization Workshops. | Agricultural equipment, Farm inputs, Seedlings, Books, Flyers and journals/Organization of sensitization Workshops. | Promotion of Agricultural Education in Schools | 75% achieved | Agricultural equipment, Farm inputs, Seedlings, Books, Flyers and journals/Organization of sensitization Workshop schools | 142,185,703.38 |
| 36 | Procurement of White Board and Pens for public Schools in the State. | White Board and Pens for public Schools in the State procured | Improve/provide good visual aid during teaching and learning sessions. | 75% achieved | White Board and Pens for public Schools in the State | 1,368,000,000.00 |
| 37 | Routine Inspection/ Monitoring visits to Schools. | Inspection/ Monitoring visits to Schools carried out. | Quality Assurance | 75% achieved | Inspection/ Monitoring visits to Schools | 142,185,703.38 |
| 38 | Conduct a 4-day Training of teachers on Special needs matters and related issues to support such pupils attain their potentials | A 4-day Training of teachers on Special needs matters and related issues to support such pupils attain their potentials conducted | Teachers’ capacity improved | 25% achieved | 4-day Training of teachers on Special needs matters and related issues to support such pupils attain their potentials | 10,000,000.00 |
| 39 | Conduct 3-day training for Teachers on Psychosocial Issues of OVC. and Security | A 3-day training for Teachers on Psychosocial Issues of OVC. and Security conducted | Impact/Increase knowledge of OVCs on trauma and its effects | 15% achieved | 3-day training for Teachers on Psychosocial Issues of OVC. and Security | 12,000,000.00 |
| 40 | Inter-school Debate competition | Inter-school competition Debate carried out | Grassroots talent hunt | 75% achieved | Inter-school debate competition | 500,000.00 |
| 41 | LGEA Debate competition | LGEA Debate competition carried out | Grassroots talent hunt | 75% achieved | LGEA debate competition | 600,000.00 |
| 42 | Zonal Debate competition | Zonal debate competition carried out | Grassroots talent hunt | 75% achieved | Zonal debate competition | 800,000.00 |
| 43 | State Debate finals | State Debate final carried out | Grassroots talent hunt | 75% achieved | State Debate final | 5,463,106.08 |
| 44 | Geopolitical Debate competition | Geopolitical debate competition carried out | develop pupils’ skills in public speaking | 75% achieved | Geopolitical Debate competition | 3,199,178.33 |
| 45 | (10 %) Set Aside for National debate Finals | National Debate Finals carried out | develop pupils’ skills in public speaking | 75% achieved | National debate Finals | 2,123,785.55 |

| S/N | ACTIVITIES | OUTPUTS | OUTCOMES | INDICATOR | OUTPUT TARGET | COSTS (NGN ‘000’) |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | 2025 | 2025 |
| 46 | Electronic Media for Debate coverage | Electronic Media used | Educate, the general public on important activities organized by SUBEB/UBEC | 75% achieved | Electronic Media | 1,554,642.59 |
| 47 | Print Media for Debate coverage | Print Media used | Educate, the general public on important activities organized by SUBEB/UBEC | 75% achieved | Print Media for Debate coverage | 500,000.00 |
| 48 | Social media for Debate coverage | Social media used | Educate, the general public on important activities organized by SUBEB/UBEC | 75% achieved | Social media for Debate coverage | 500,000.00 |
|  | QUALITY AND EFFICIENCY SUB-TOTAL |  |  |  |  | 8,380,713,537 |

4.3	POLICY 3: SYSTEM STRENGHTENING AND EFFICICIENCY

4.3.1	POLICY OBJECTIVE: To ensure proper coordination for development and management of Public Basic Education in Benue State.

Table 4.4: System Strengthening and Efficiency

| S/N | ACTIVITIES | OUTPUTS | OUTCOMES | INDICATOR | OUTPUT TARGET | COSTS (NGN ‘000’) |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | 2025 | 2025 |
| 1 | Conducting capacity building for 30 EMIS staff at SUBEB Headquarters | 30 EMIS staff at SUBEB Headquarters trained | Improve Data collection/quality and record keeping | 75% achieved | 30 EMIS staff at SUBEB Headquarters | 3,060,000.00 |
| 2 | Activate and Maintain EMIS at the 23-LGEAs of Benue State | EMIS at the 23-LGEAs of Benue State activated | Improve Data collection/quality and record keeping | 75% achieved | EMIS at the 23-LGEAs of Benue State | 115,000,000.00 |
| 3 | 3-Day Training of 46 SUBEB/LGEA Enumerators for ASC/On Line Completion of ASC | Training of SUBEB/LGEA Enumerators for ASC/On Line Completion of ASC carried out | Improve quality and integrity of Data | 75% achieved | 46 SUBEB/LGEA Enumerators for ASC/On Line Completion of ASC | 10,000,000.00 |
| 4 | Conduct of Annual School Census (ASC) | 21 days Annual School census conduct on-line carried out | Improve quality and integrity of Data | 75% achieved | 46 Enumerators & 15 supervisors | 25,000,000.00 |
| 5 | 1 No. TOYOTA HILUX Van 2025 Model | 1 No. TOYOTA HILUX VAT 2025 Model purchased | For effective coverage of CQA areas | 75% achieved | 1 No. TOYOTA HILUX VAT/WHT | 149,779,220.47 |
| 6 | Procurement of 33 All-in-One HP Desktop Computers | 33 All-in-One HP Desktop Computers procured | To provide PRS Officers with functional digital tools for enhanced field work | 75% achieved | 33 All-in-One HP Desktop Computers | 21,450,000 |
| 7 | Procurement of 30 Motorcycles for QA Officers | 30 Motorcycles for QA Officers procured | To convey QA staff for effective monitoring at the LGEAs | 75% achieved | 30 Motorcycles for QA Officers | 2,837,500 |
| 8 | Conduct a review of 2024 to 2027 MTBESP, Publication and distribution of 200 copies to relevant stakeholders | 2024 to 2027 MTBESP reviewed. | sustained yearly strategic planning | 50% achieved | 2024 to 2027 MTBESP | 7,000,000 |
|  | SYSTEM STRENGTHENING SUB-TOTAL |  |  |  |  | 334,126,720.47 |

5.0	SUMMARY OF POLICY OBJECTIVE COSTS

Table 5.1: Cost Summary for Financing Benue SUBEB Work Plan by Policy Objectives

| S/N | POLICY OBJECTIVE | COSTS (NGN ‘000’) |
| --- | --- | --- |
|  |  | 2025 |
| 1 | ACEESS, EQUITY AND INCLUSIVENESS - SUB TOTAL | 10,173,122,568.27 |
| 2 | QUALITY AND EFFICIENCY - SUB TOTAL | 8,380,713,537.43 |
| 3 | SYSTEM STRENGTHENING AND EFFICIENCY - SUB TOTAL | 334,126,720.47 |
|  | GRAND TOTAL | 18,887,962,826.17 |

6.0	ASSUMPTIONS AND COSTS PROJECTIONS

Assumptions and cost projections in this work plan aim to predict the future of the economy on a broad scale; also help for informed decisions to build the plan, though difficult and impossible situations are inevitable. We shall be leveraging on these other factors affecting the plans cost projections:

- The general inflationary cost in recent times.

- UBEC/SUBEB matching grant will be accessed.

- UNICEF will contribute their supports.

- Allocations from all levels will be release duly.

- The Internally Generated Revenue (IGR) for the State will be on a rise.

- Improved insecurity/security in the State and Nation is expected.

- Unstable political will, shall be adequately managed.

7.0	COST OF THE SUB-SECTOR PLAN FOR BENUE SUBEB WORK PLAN

Table 6: Sub-Sector Plan Costs for Benue SUBEB Work Plan of year 2025

| KEY EXPENDITURE AREARS | COMPONENTS | COSTS (NGN ‘000’) |
| --- | --- | --- |
|  |  | 2025 |
| ACCESS EQUITY & INCLUSIVNESS | Out of School | 44,000,000.00 |
|  | Girl Child Education (Gender Equality) | 25,000,000.00 |
|  | Physical Infrastructure; Construction, Rehabilitation & Drilling Borehole | 5,336,401,667.20 |
|  | Furniture; Tables/Chairs & Plastic Seaters | 4,617,941,680.60 |
|  | Toyota Hilux Van | 149,779,220.47 |
| TOTAL |  | 10,173,122,568.27 |
| QUALITY AND EFFICIENCY | Teacher Professional Development (TPD), Trainings, Sensitization and Workshops | 1,114,600,000.20 |
|  | Quality Assurance | 3,711,488,075.76 |
|  | Monitoring Learning Achievement (MLA) & Early Reading and Numeracy | 722,400,000.00 |
|  | Recruitment and Deployment of Teachers | 1,552,000,000.00 |
|  | Sports/Recreation | 93,402,707.20 |
|  | Agriculture | 142,185,703.38 |
|  | Social Media | 5,109,285.18 |
|  | Debate | 12,686,069.96 |
|  | Basic Education Curriculum | 99,529,992.37 |
|  | GSCCI - Greening | 118,592,851.69 |
|  | Safeguards/Waste Management | 23,592,851.69 |
|  | Production of Unified/Same Uniforms for Pupils | 785,126,000.00 |
| TOTAL |  | 8,380,713,537.43 |

| KEY EXPENDITURE AREARS | COMPONENTS | COSTS (NGN ‘000’) |
| --- | --- | --- |
|  |  | 2025 |
| SYSTEM STRENGTHENING | Annual School Census (ASC) | 35,000,000.00 |
|  | Education Management Information System (EMIS) | 139,510,000.00 |
|  | MTBESP | 7,000,000.00 |
|  | Toyota Hilux Van | 149,779,220.47 |
|  | MotorCycles | 2,837,500.00 |
| TOTAL |  | 334,126,720.47 |
| GRAND TOTAL |  | 18,887,962,826.17 |

8.0	RISKS AND MITIGATION MEASURES

Basically, to consider what could go wrong in such a plan is regular. That is, things that can negatively impact the budget performance and timeline or output of Benue Work Plan 2025 for the state are much obvious.

Therefore, planning on mitigating the likely risks of the plan is vital, aiming at reducing, avoiding, controlling, transferring/sharing/diversifying and monitoring well known threats to the Benue Work Plan - 2025 for a sure budget delivery within standards.

The risks are identified with probability positions and impact levels, while mitigating strategies are outline for Monitoring and Evaluating.

Risks and mitigation measures table:

| IMPACT | High | 3 | 6 | 9 |
| --- | --- | --- | --- | --- |
|  | Medium | 2 | 4 | 6 |
|  | Low | 1 | 2 | 3 |
|  |  | Low | Medium | High |
|  | PROBABILITY |  |  |  |

Table 7: Risks, Probability, Impact and Mitigating Strategies for Benue SUBEB Work Plan – 2025

| S/N | Risks | Probability | Impact | Mitigation strategies |
| --- | --- | --- | --- | --- |
| 1 | Enrolment Supply Risk | 6 | * Out-of-School & Dropout Gaps. | * Sensitization for school returning and enrolment. |
|  |  |  | * Under-utilization of facilities. | * General Enrolment of Pupils in to our Public Basic Education. |
|  |  |  | * Wastage to Resources. | * Provision/creation of adequate infrastructures/facilities/material for pupils in Public Basic Education System. |
|  |  |  |  | * Employment of more Staff/Teachers. |
| 2 | School Safety/Disaster/Security Risk | 9 | * Insecurity in Benue State. | * Conflict resolution and dialog for mitigation. |
|  |  |  | * Steady Herders/Farmers crisis. | * Crisis management planning/practice. |
|  |  |  | * Frequent Communal Crisis | * Emergency measures - Security personnel. |
|  |  |  | * Annual flood disaster. | * Consultation with government to build drainages required places. |
|  |  |  | * Out-of-School & Dropout rate gaps. | * Trainings on Crisis management. |
|  |  |  |  | * Fencing of School to reduce attacks. |
| 3 | Poor Funding Risk | 3 | * Affects timely planning &implementations. | * Ensure/facilitate for on time planning &implementations. |
|  |  |  | * Quality Data provision & availability deficiency. | * Ensure/facilitate for quality data availability. |
|  |  |  | * Poor Research funding. | * Ensure availability of funds for research findings/resolutions. |
|  |  |  | * M&E actualization deficiency. | * Ensure effective M&E. |
|  |  |  | * Hampers duty Mobility & Mobilization. | * Ensure allocation of funds for mobility & mobilization. |
|  |  |  | * Lack of accountability. | * Improve accountability. |
| 4 | Political Risk | 2 | * Government will challenge. | * Increase advocacy with Governor/political actors/critical stakeholders. |
|  |  |  | * Untimely implementations. | * Government timely budget release/implementation. |
|  |  |  | * Delay in budget release | * Keep concern/planning team focused. |
| 5 | Economic/Financial risk | 6 | * Inflation in costs. | * Relieve provision by government. |
|  |  |  | * Partners reverse decisions. | * Memorandum of Understanding be signed by concerned partners. |
|  |  |  | * Untimely matching of UBEC/SUBEB counterpart funds. | * Flexibility of UBEC & other related bodies of counterpart funding and assistance. |
|  |  |  | * Barrier to enhancing progress due to lack of resources. | * Benue State Government prioritizing payments of concern to Public Basic Education. |
|  |  |  | * Exponential rise of operations costs. | * Advocacy for an increase of budget/allocation to Public Education Sector. |
|  |  |  | * Lack of accountability. | * Improve accountability. |
| 6 | Equity Risk | 4 | * Gender Parity Index Gap | * Enrolment of more Girl child in to our Puplic Basic Education. |
|  |  |  | * Widen gap in facilities/material to pupil’s ratio. | * General Enrolment of Pupils in to our Public Basic Education. |
|  |  |  | * Out-of-School & Dropout rates gaps. | * Provision/creation of adequate facilities/material for pupils in Public Basic Education System. |

| S/N | Risks | Probability | Impact | Mitigation strategies |
| --- | --- | --- | --- | --- |
| 7 | Staffing/Transfer/Retirement Risk | 4 |  |  |
|  |  |  | * Wide Teacher-Pupils Ratio gap. | * Employment of Staff/Teachers. |
|  |  |  | * Stress effects on the staff/teacher. | * Increase efficiency/effectiveness. |
|  |  |  | * Under-Utilization of staff/teacher. | * General Enrolment of Pupils in to our Public Basic Education. |
|  |  |  | * Miss-understanding/Mix-up/Delay in implementation plan. | * Maintain/retaining concern staff & to train others on the job. |
|  |  |  | * Lack of experience/No training of other personnel. | * Sensitization for school returning and enrolment. |
|  |  |  | * Dropout rate widen. |  |
| 8 | Compliance/Reputation Risk | 6 | * Loss of funding. | * Utilization of funds on actual purposes. |
|  |  |  | * Loss of credibility. | * Improve financial credibility by effective & efficient management of finances. |
|  |  |  | * Lack of control. | * Adherence to plan and policy objectives and procedures. |
|  |  |  | * Legal action. | * Control measures to curb abuse of accreditation. |
|  |  |  |  | * Considerations to legislative guilds were necessary. |

9.0	MONITORING AND EVALUATION

Monitoring and Evaluation (M&E) here is a systematic on-going guild to collecting and analysing of data to assess the effectiveness and impact of this work plan. M&E as a living section regularly tracks results and indicators throughout the life of the plan and dissemination of reports to relevant authorities, departments, sections, units and officers for improvement.

Monitoring and Evaluation (M&E) system covers all the works carried out all through this plan. Here, everything comes together, from the initial selection of objectives, activities, indicators, outputs and outcomes through to the final evaluation of this plan.

The M&E system involves the SUBEB office with the departments (units involving), LGEA office with the departments (units involving), schools with the head-teachers/teachers involving, and learners. They are saddled with progress reports responsibility; on monthly, quarterly or annual bases for analysing efficiency and effectiveness.

10.0	KEY PERFORMANCE INDICATORS

Key Performance Indicators (KPIs) are the measurable critical quantifiable metrics used to evaluate and assess progress toward an intended result. KPIs provide a focus for strategic and operational improvement, creating an analytical basis for decision making, with attention on what matters most.

Table 8: Work Plan - 2025 Key Performance Indicators

| Indicator Name | Unit of Measurement | B/LINE - 2024 | Target - 2025 | Data Source/Means of verification | Responsibility for Data Collection |
| --- | --- | --- | --- | --- | --- |
|  | Access, Equity and Inclusiveness |  |  |  |  |
| Pre-Primary Gross Enrolment Rate Total | % | 39.62% | 11.75% | NPA, 2022 | UBEC/SUBEB/MoE&KM |
| Pre-Primary Gross Enrolment Rate Boys | % | 10.62% | 1.43% | NPA, 2022 | UBEC/SUBEB/MoE&KM |
| Pre-Primary Gross Enrolment Rate Girls | % | 9.19% | 10.32% | NPA, 2022 | UBEC/SUBEB/MoE&KM |
| Primary Gross Enrolment Rate Total | % | 69.19% | 7.70% | NPA, 2022 | UBEC/SUBEB/MoE&KM |
| Primary Gross Enrolment Rate Boys | % | 43.43% | 1.10% | NPA, 2022 | UBEC/SUBEB/MoE&KM |
| Primary Gross Enrolment Rate Girls | % | 25.76% | 6.60% | NPA, 2022 | UBEC/SUBEB/MoE&KM |
| JSS Gross Enrolment Rate Total | % | 45.56% | 10% | NPA, 2022 | UBEC/SUBEB/MoE&KM |
| JSS Gross Enrolment Rate Boys | % | 25.88% | 1.80% | NPA, 2022 | UBEC/SUBEB/MoE&KM |
| JSS Gross Enrolment Rate Girls | % | 19.68% | 8.20% | NPA, 2022 | UBEC/SUBEB/MoE&KM |
| Primary Gross Intake Rate Total | % | 28.11% | 5.50% | NPA, 2022/NPoCN, 2022 Projected | UBEC/SUBEB/MoE&KM |
| Primary Gross Intake Rate Boys | % | 28.71% | 5.50% | NPA, 2022/NPoCN, 2022 Projected | UBEC/SUBEB/MoE&KM |
| Primary Gross Intake Rate Girls | % | 27.51% | 6.50% | NPA, 2022/NPoCN, 2022 Projected | UBEC/SUBEB/MoE&KM |
| Primary 1 Repetition Rate Total | % | 3,108 | 777 | NPA, 2022 | UBEC/SUBEB/MoE&KM |
| Primary 1/ Primary 2 Retention Rate Total | % |  |  |  |  |
| Primary 2/ Primary 3 Retention Rate Total | % |  |  |  |  |
| Primary 3/ Primary 4 Retention Rate Total | % |  |  |  |  |
| Primary 4/ Primary 5 Retention Rate Total | % |  |  |  |  |
| Primary 5/ Primary 6 Retention Rate Total | % |  |  |  |  |
| Primary to JSS Transition Rate Total | % | 82.6% | 4.3% | NPA, 2022 | UBEC/SUBEB/MoE&KM |
| Primary to JSS Transition Rate Boys | % | 71.9% | 6.5% | NPA, 2022 | UBEC/SUBEB/MoE&KM |

| Indicator Name | Unit of Measurement | B/LINE - 2024 | Target - 2025 | Data Source/Means of verification | Responsibility for Data Collection |
| --- | --- | --- | --- | --- | --- |
| Primary to JSS Transition Rate Girls | % | 95.1% | 1.2% | NPA, 2022 | UBEC/SUBEB/MoE&KM |
| JSS 1/JSS2 Retention Rate Total | % |  |  |  |  |
| JSS 2/JSS3 Retention Rate Total | % |  |  |  |  |
| Primary Education Completion Rate Total | % | 44.38% | 10.50% | NPA, 2022 | UBEC/SUBEB/MoE&KM |
| Primary Education Completion Rate Boys | % | 47.75% | 10.5% | NPA, 2022 | UBEC/SUBEB/MoE&KM |
| Primary Education Completion Rate Girls | % | 41.11% | 13.5% | NPA, 2022 | UBEC/SUBEB/MoE&KM |
| GPI Pre-Primary | Ratio | 0.91 | 0.01 | NPA, 2022 | UBEC/SUBEB/MoE&KM |
| GPI Primary | Ratio | 0.94 | 0.02 | NPA, 2022 | UBEC/SUBEB/MoE&KM |
| GPI JSS | Ratio | 0.86 | 0.025 | NPA, 2022 | UBEC/SUBEB/MoE&KM |
| JS Education Completion Rate Total | % | 29.98% | 10% | NPA, 2022 | UBEC/SUBEB/MoE&KM |
| JS Education Completion Rate Boys | % | 17.31% | 4.64% | NPA, 2022 | UBEC/SUBEB/MoE&KM |
| JS Education Completion Rate Girls | % | 12.67% | 5.36% | NPA, 2022 | UBEC/SUBEB/MoE&KM |
|  | Quality and Efficiency |  |  |  |  |
| Pre-Primary Pupil / Classroom | Ratio | 01:46 | 01:44 | NPA, 2022 | UBEC/SUBEB/MoE&KM |
| Primary Pupil / Classroom | Ratio | 0.084 | 0.083 | NPA, 2022 | UBEC/SUBEB/MoE&KM |
| JSS Pupil / Classroom | Ratio | 01:58 | 01:56 | NPA, 2022 | UBEC/SUBEB/MoE&KM |
| Pre-Primary Pupil / Teacher | Ratio | 01:39 | 01:37 | NPA, 2022 | UBEC/SUBEB/MoE&KM |
| Pre-Primary Pupil / Teacher Urban | Ratio | 1:75 | 1:71 | NPA, 2022 | UBEC/SUBEB/MoE&KM |
| Pre-Primary Pupil / Teacher Rural | Ratio | 1:77 | 1:73 | NPA, 2022 | UBEC/SUBEB/MoE&KM |
| Primary Pupil / Teacher | Ratio | 01:40 | 01:38 | NPA, 2022 | UBEC/SUBEB/MoE&KM |
| Primary Pupil / Teacher Urban | Ratio | 1:65 | 1:61 | NPA, 2022 | UBEC/SUBEB/MoE&KM |
| Primary Pupil / Teacher Rural | Ratio | 1:41 | 1:37 | NPA, 2022 | UBEC/SUBEB/MoE&KM |
| JSS Student / Teacher | Ratio | 01:28 | 01:26 | NPA, 2022 | UBEC/SUBEB/MoE&KM |

| Indicator Name | Unit of Measurement | B/LINE - 2024 | Target - 2025 | Data Source/Means of verification | Responsibility for Data Collection |
| --- | --- | --- | --- | --- | --- |
| JSS Student / Teacher Urban | Ratio | 1:39 | 1:35 | NPA, 2022 | UBEC/SUBEB/MoE&KM |
| JSS Student / Teacher Rural | Ratio | 1:32 | 1:28 | NPA, 2022 | UBEC/SUBEB/MoE&KM |
| Proportion of qualified teachers Pre-primary | % | 85.45% | 2.50% | NPA, 2022 | UBEC/SUBEB/MoE&KM |
| Proportion of qualified teachers Primary | % | 88.50% | 1.20% | NPA, 2022 | UBEC/SUBEB/MoE&KM |
| Proportion of qualified teachers JSS | % | 86.45% | 2% | NPA, 2022 | UBEC/SUBEB/MoE&KM |
| Proportion of Primary learners that have access to textbooks-English | % | 56.50% | 5% | NPA, 2022 | UBEC/SUBEB/MoE&KM |
| Proportion of Primary learners that have access to textbooks-Mathematics | % | 60.48% | 5% | NPA, 2022 | UBEC/SUBEB/MoE&KM |
| Proportion of Primary learners that have access to textbooks-Basic Science and Technology | % | 52.50% | 5% | NPA, 2022 | UBEC/SUBEB/MoE&KM |
| Proportion of Primary learners that have access to textbooks-Social Studies | % | 55.65% | 5% | NPA, 2022 | UBEC/SUBEB/MoE&KM |
| Proportion of JS students that have access to textbooks-English | % | 35.82% | 5% | NPA, 2022 | UBEC/SUBEB/MoE&KM |
| Proportion of JS students that have access to textbooks-Mathematics | % | 38.85% | 5% | NPA, 2022 | UBEC/SUBEB/MoE&KM |
| Proportion of JS students that have access to textbooks-Basic Science and Technology | % | 42.25% | 5% | NPA, 2022 | UBEC/SUBEB/MoE&KM |
| Proportion of JS students that have access to textbooks-Social Studies | % | 31.85% | 5% | NPA, 2022 | UBEC/SUBEB/MoE&KM |
| MLA P2 Literacy Mean score | % |  |  |  |  |
| MLA P2 Numeracy Mean score | % |  |  |  |  |
| MLA P4 Literacy Mean score | % |  |  |  |  |
| MLA P4 Numeracy Mean score | % |  |  |  |  |
| MLA P5 or 6 Literacy Mean score | % | 509.90% | 0.2% | NALABE, 2022 | UBEC/SUBEB |
| MLA P5 or P6 Numeracy Mean score | % | 498.69% | 0.3% | NALABE, 2022 | UBEC/SUBEB |
| BECE Pass rate (6 credits including English and Mathematics) | % |  |  |  |  |

| Indicator Name | Unit of Measurement | B/LINE - 2024 | Target - 2025 | Data Source/Means of verification | Responsibility for Data Collection |
| --- | --- | --- | --- | --- | --- |
| Proportion of Primary schools with access to Good Water source | % | 43.75% | 10% | NPA, 2022 | UBEC/SUBEB/MoE&KM |
| Proportion of JSS with access to good Water source | % | 55% | 8% | NPA, 2022 | UBEC/SUBEB/MoE&KM |
| Pupil/Toilet Primary Ratio | Ratio | 01:45 | 01:39 | NPA, 2022 | UBEC/SUBEB/MoE&KM |
| Pupil/Toilet JSS Ratio | Ratio | 01:20 | 01:16 | NPA/ASC/M&E REPORTS | UBEC/SUBEB/MoE&KM |
| Proportion of Schools with separate toilets for Boys and Girls Primary | % |  |  |  |  |
| Proportion of Schools with separate toilets for Boys and Girls JSS | % |  |  |  |  |
| Primary Schools with Library Primary | % | 12.56% | 10% | NPA/ASC/M&E REPORTS | UBEC/SUBEB/MoE&KM |
| JS Schools with Library JSS | % | 44.37% | 10% | NPA/ASC/M&E REPORTS | UBEC/SUBEB/MoE&KM |
| Proportion of Schools with Access to ICT facilities Primary | % |  |  |  |  |
| Proportion of Schools with Access to ICT facilities JSS | % |  |  |  |  |
| Proportion of Schools with Access to Power Primary | % | 8.58% | 10% | NPA/ASC/M&E REPORTS | UBEC/SUBEB/MoE&KM |
| Proportion of Schools with Access to Power JSS | % | 39.99% | 10% | NPA/ASC/M&E REPORTS | UBEC/SUBEB/MoE&KM |
| Proportion of schools with fencing Primary | % | 5.85% | 10% | NPA/ASC/M&E REPORTS | UBEC/SUBEB/MoE&KM |
| Proportion of schools with fencing JSS | % | 15.73% | 10% | NPA/ASC/M&E REPORTS | UBEC/SUBEB/MoE&KM |
| Proportion of Primary learners that have access to furniture (chair/table/desk) | % | 45.75% | 10% | NPA/ASC/M&E REPORTS | UBEC/SUBEB/MoE&KM |
| Proportion of JS students that have access to furniture (chair/table/desk) | % | 58.97% | 10% | NPA/ASC/M&E REPORTS | UBEC/SUBEB/MoE&KM |
| Proportion of JS schools That that have to Laboratories | % | 38% | 10% | NPA/ASC/M&E REPORTS | UBEC/SUBEB/MoE&KM |

11.0	CONCLUSION

With the goal of providing free education to all children in Nigeria, Benue SUBEB Work Plan - 2025 serves as a roadmap charting the course for the year 2025, of which Benue basic education financing, assumptions/cost projections, risks/mitigation measures, monitoring/evaluation, and progress reporting as well as assessment will reach new horizons for successful implementation of the Work Plan in the state. Inevitably, challenges and gaps in aspects of pupils’ enrolment, Out of School Children (OOSC), special needs situations, gender imbalance, inadequate teachers, facilities, structures, infrastructures and instructional materials are adequately addressed for a continuous Monitoring and Evaluation.

The resources and costs estimate for the Benue SUBEB Work Plan - 2025 is N18,887,962,826.17. Provision is made for M&E as well as review of the plan and improvement upon implementation, with adequate measures addressing ineffective and inefficient planning, taking advantage of strengths and existing opportunities, while mitigating the risks.